## Sheet1
Week # | Project |  | Time Allocated | Chapter | Dissertation | Time Allocated |  | Special date
3
4 |  | Administration issues | 2 |  | Introduction lecture 2016-01-27 -- 9A 312 | 2
5 | Sprint 1 | Enviromental setup and instalation | 20 |  | Report setup, Planing, LaTeX skeleton, Diary | 10
|  | Meetings with eSense team | 6 |  | Info Search lecture 2016-02-03 -- Biblioteket | 2
6 |  | Literature studdies and background reading | 30 |  | Dissertation lecture 2016-02-10 -- 21A 347 | 2
|  | eSense, Continua, reference cases |  | 2 | Outline report and chapter 2 (Background) | 10
7 | Sprint 2 | Assess pros and cons for mobile as gateway | 20 |  | Draft chapter 2 | 20
pros and cons for selection of OS
8 |  | Look for open source for connection of | 30 |  | Final draft chapter 2 | 10
multiple devices to mobile phone over
bluetooth
Set up developing enviroment and try open
open source solutions
9 | Sprint 3 | Start design of implementation | 30 | 3 | Outline chapter 3 (Design) | 10 |  | 2016-03-09 Progress report #1 DUE
10 |  | Finish design of implementation | 10 |  | Draft chapter 3 | 30
11 | Sprint 4 | Start implementation of prototype and | 30 |  | Final draft chapter 3 | 10
litterature studdies.
12 |  | Coding mobile gateway | 30 | 4 | Outline chapter 4 (Implementation) | 10
13 | Sprint 5 | Coding mobile gateway | 20 |  | Draft chapter 4 | 20
14 |  | Coding integration to eSense | 30 |  | Final draft chapter 4 | 10 |  | 2016-04-14 Progress report #2 DUE
15 | Sprint 6 | Coding integration to eSense | 30 | 5 | Draft chapter 5 (Result) | 10
16 |  | Coding | 10 |  | Final draft chapter 5 | 30
17 | Sprint 7 | Final collage of evaluation | 20 | 6 | Draft chapter 6 (Evaluation) | 20
18 |  | Coding supplemental functionality | 10 |  | Final draft chapter 6 | 30 |  | 2016-05-06 Progress report #3 DUE
map localization
19 | Sprint 8 | Final version of prototype | 30 | 1 | Draft chapter 1 (Introduction) | 10
20 |  | Coding supplemental functionality | 10 |  | Final draft chapter 1 | 30 |  | 2016-05-20 FINAL Dissertation DUE
map localization
21 | Demo | Demo prototype, present findings | 10 | 1-6 | Proof reading and final version of dissertation | 30
22 |  |  |  |  | Reading opponents dissertation + opp report | 38 |  | 2016-06-03 Opposition presentation
[5 empty] | Defending dissertation and Opponing dissertation | 2 |  | 2016-06-03 Progress report #4 DUE
2016-06-03 Opposition report DUE
23 |  |  |  |  | Final adjustments | 20
24 |  |  |  |  | Final adjustments | 20 |  | 2016-06-20 FINAL FINAL Dissertation DUE
Total |  |  | 378 |  |  | 386 | 764